## 1. Master Plan
Sheet 1: Master Plan ¦ Org Design / Ways of Working
Combined project + change management milestones for your Org Design / Ways of Working. One row per milestone. Update status weekly in your project stand-up.
# | Milestone | Type | Phase | Owner | Target date | Actual date | Status | Notes / blockers
1 | Design Rationale & Executive Alignment | Project | Initiation | [Owner] | [Date] |  | Not started
2 | CM Approach & People Risk Assessment | CM | Initiation | [Owner] | [Date] |  | Not started
3 | Future State Design Completed | Project | Planning | [Owner] | [Date] |  | Not started
4 | Impacted Employee Communication Sequencing Planned | CM | Planning | [Owner] | [Date] |  | Not started
5 | Legal Consultation Process Completed | Project | Design & Build | [Owner] | [Date] |  | Not started
6 | Individual 1:1 Conversations Completed | CM | Design & Build | [Owner] | [Date] |  | Not started
7 | All-Staff Announcement & New Structure Communicated | Project | Design & Build | [Owner] | [Date] |  | Not started
8 | Role Clarity & Team Norming Sessions | CM | Testing | [Owner] | [Date] |  | Not started
9 | Operating Model & Ways of Working Defined | Project | Testing | [Owner] | [Date] |  | Not started
10 | New Structure Goes Live | Project | Go-live | [Owner] | [Date] |  | Not started
11 | Hypercare: Pulse Checks & Manager Coaching | CM | Go-live | [Owner] | [Date] |  | Not started
12 | Culture & Performance Alignment Review | Project | Post Go-live | [Owner] | [Date] |  | Not started
13 | Ways of Working Embedded & Transitioned to BAU | CM | Post Go-live | [Owner] | [Date] |  | Not started

## 2. Stakeholder Register
Sheet 2: Stakeholder Register ¦ Org Design / Ways of Working
Track every stakeholder for your Org Design / Ways of Working. Update monthly and after every key conversation.
Stakeholder name | Team / role | Change type | Impact level | Engagement approach | Key concerns | Owner | Last contact | Status | Notes
[Name] | Executive sponsor | Org Design / Ways of Working | High | Monthly sponsor review | Strategic alignment, budget | PM | [Date] | Not started
[Name] | Team manager A | Org Design / Ways of Working | High | Weekly briefing | Team readiness, concerns | Change lead | [Date] | Not started
[Name] | Frontline staff rep | Org Design / Ways of Working | High | Focus groups + Q&A | Job impact, workload | Change lead | [Date] | Not started
[Name] | HR partner | Org Design / Ways of Working | High | Bi-weekly | People risk, morale | Change lead | [Date] | Not started
[Name] | IT / tech lead | Org Design / Ways of Working | Medium | Bi-weekly WIP | Technical dependencies | PM | [Date] | Not started
[Name] | Change champion A | Org Design / Ways of Working | Medium | Bi-weekly champion call | Peer resistance | Change lead | [Date] | Not started

## 3. Comms Tracker
Sheet 3: Comms Tracker ¦ Org Design / Ways of Working
Plan and track every communication for your Org Design / Ways of Working from kick-off to BAU.
Communication title | Audience | Channel | Owner | Planned date | Sent date | Status | Key message | Link to asset
Project / change announcement | All staff | Email + intranet | Exec sponsor | [Date] |  | Not started | Why this change, what comes next | [Link]
Manager briefing pack | All managers | Teams meeting + PDF | Change lead | [Date] |  | Not started | Impact by team, how to support staff | [Link]
FAQ published | All staff | Intranet | Change lead | [Date] |  | Not started | Top 10 anticipated questions answered | [Link]
Training dates confirmed | All impacted | Email | Training lead | [Date] |  | Not started | When, how, and what to expect | [Link]
4-week countdown | All impacted | Email + Teams | Comms lead | [Date] |  | Not started | Progress update, final prep reminder | [Link]
Go-live announcement | All users | Email + Teams | Exec sponsor | [Date] |  | Not started | We are live — here is where to get help | [Link]
Hypercare week 1 bulletin | All users | Email | Change lead | [Date] |  | Not started | Known issues, workarounds, support | [Link]
Post go-live survey | All impacted | Survey link | Change lead | [Date] |  | Not started | How is it going? What do you still need? | [Link]
Month 2 adoption update | All staff | Email | Change lead | [Date] |  | Not started | Adoption metrics, success stories | [Link]
BAU handover announcement | All staff | Email | Business owner | [Date] |  | Not started | Project closing — here is who to contact | [Link]

## 4. Training Tracker
Sheet 4: Training Tracker ¦ Org Design / Ways of Working
Track training design, delivery, and completion for your Org Design / Ways of Working. Completion % auto-calculates.
Training module | Audience | Format | Duration | Owner | Delivery date | # Invited | # Completed | Completion % | Status | Notes
Overview: why this change | All staff | Email / video | 5 min | Change lead | [Date] |  |  |  | Not started | Send before any detailed training
Manager briefing | All managers | Live workshop | 60 min | Change lead | [Date] |  |  |  | Not started | Run before all-staff sessions
Role training: [Role A] | [Team A] | Workshop / sandbox | 2 hrs | Training lead | [Date] |  |  |  | Not started | Role-specific tasks only
Role training: [Role B] | [Team B] | Workshop / sandbox | 90 min | Training lead | [Date] |  |  |  | Not started
Quick reference guide | All users | PDF / intranet | Self-serve | Training lead | [Date] | N/A | N/A | N/A | Not started | Publish 2 wks pre go-live
Refresher drop-in | All users | Live webinar | 30 min | Training lead | [Date] |  |  |  | Not started | Week 2 of hypercare
New-starter induction (BAU) | New starters | E-learning | 45 min | Training lead | [Date] | N/A | N/A | N/A | Not started | Update before project closes

## 5. Hypercare Log
Sheet 5: Hypercare Log ¦ Org Design / Ways of Working
Log every issue and query raised during hypercare. Review daily. Close only when exit criteria are met.
# | Date raised | Issue / query | Raised by | Team | Category | Priority | Owner | Resolution / action | Status | Date resolved | Comms needed?
1 | [Date] | [Describe issue clearly] | [Name] | [Team] | System / process issue | High | [Owner] | [Action] | Not started |  | Yes
2 | [Date] | [Describe query clearly] | [Name] | [Team] | Training gap | Medium | Change lead | [Action] | In progress |  | Yes
3 | [Date] | [Describe query clearly] | [Name] | [Team] | Process / policy question | Low | Process owner | [Action] | Complete | [Date] | No
4 | [Date] | [Describe issue clearly] | [Name] | [Team] | Access / data issue | High | IT / HR lead | [Action] | Not started |  | Yes

## 6. Adoption Tracker
Sheet 6: Adoption Tracker ¦ Org Design / Ways of Working
Weekly adoption metrics after go-live. Target 80% adoption by week 4. Update every Friday.
Period | Active users | Total users | Adoption % | Issues raised | Issues resolved | Issues outstanding | Sentiment (1–5) | Actions this week | RAG
Week 1 (go-live) | [7 empty] | Hypercare team active. Daily stand-up.
Week 2 | [7 empty] | Drop-in session. FAQ update.
Week 3 | [7 empty] | Manager pulse check.
Week 4 | [7 empty] | Review hypercare exit criteria.
Month 2 | [7 empty] | Post-implementation review.
Month 3 | [7 empty] | BAU transition check.
Month 6 health check | [7 empty] | Spot-check with 5 users.

## 7. Risk & Issues Log
Sheet 7: Risk & Issues Log ¦ Org Design / Ways of Working
Track risks to your Org Design / Ways of Working change management plan. Review weekly with the PM.
# | Type | Risk / issue description | Impact if occurs | Likelihood | Severity | Owner | Mitigation / action | Status | Review date | Notes
1 | Risk | Exec sponsor not visible or active | Low buy-in and adoption failure | Medium | High | Change lead | Weekly sponsor check-in. Agreed comms schedule. | Not started | [Date]
2 | Risk | Stakeholders not engaged early enough | Resistance and surprises at go-live | Medium | High | Change lead | Stakeholder mapping complete by week 4. | Not started | [Date]
3 | Risk | Training delivered too close to or after go-live | Low confidence, high support volume | Medium | High | Training lead | Training complete 2 weeks before go-live. | Not started | [Date]
4 | Risk | Communications inconsistent or too infrequent | Rumour, anxiety, and loss of trust | Medium | Medium | Comms lead | Comms calendar published. No gap >2 weeks. | Not started | [Date]
5 | Risk | No change champions identified | Peer resistance spreads unchecked | Low | Medium | Change lead | Champions confirmed by month 2. | Not started | [Date]
6 | Risk | Go-live date changes after training delivered | Knowledge gap at go-live | Low | Medium | PM | Refresher plan ready if date shifts. | Not started | [Date]
7 | Issue | [Current issue description] | [Impact if not resolved] |  | High | [Owner] | [Action being taken] | Not started | [Date]

## 8. README
Sheet 8: README ¦ Org Design / Ways of Working
How to set up and use this Smartsheet workspace.
Section | Detail
WORKSPACE SETUP | Create a Smartsheet workspace: '[Project name] — Change Management'. Add each sheet as a separate grid tab.
Sheet 1: Master Plan | Top-level tracker. Update Status before every weekly stand-up. Both project and CM milestones live here.
Sheet 2: Stakeholder Register | Review monthly. Update 'Key concerns' after every conversation. High impact stakeholders need personal engagement.
Sheet 3: Comms Tracker | Every communication planned here first. Link all draft assets. No communication goes out without a row in this sheet.
Sheet 4: Training Tracker | Completion % auto-calculates. Escalate any group below 80% one week before go-live.
Sheet 5: Hypercare Log | Open on go-live day. Every issue gets a row. Review daily in the 15-minute hypercare stand-up.
Sheet 6: Adoption Tracker | Update every Friday. Share with exec sponsor. Define 'active user' before go-live.
Sheet 7: Risk & Issues Log | Review High risks weekly. Escalate to sponsor if not progressing. Never delete rows — archive with a note.
COLOUR CODING | Not started (grey) ¦ In progress (amber) ¦ Complete (green) ¦ At risk (red) ¦ High (red) ¦ Medium (amber) ¦ Low (green)
SMARTSHEET TIPS | Use Automations to send reminders on target dates. Build a Dashboard from Sheet Summaries for exec reporting. Link sheets using cross-sheet formulas.
PRO HUMANITATE | Wake Forest University ¦ brand.wfu.edu