## Communications Plan
Communications Plan ¦ Wake Forest University
Plan every communication from kick-off to BAU. No comms sent without a row here.
Communication title | Audience | Channel | Approved by | Owner/sender | Draft due | Planned send date | Actual send date | Status | Key message (one line) | Link to asset
Project kick-off email | Project team | Email | Exec sponsors | Exec sponsors | [Date] | [Date] |  | Not started | Why this project, who is on the team, what to expect | [Link]
Stakeholder announcement | SBAs and ITPs | Email | Exec sponsors | Exec sponsors | [Date] | [Date] |  | Not started | What is changing, why, and how it affects you | [Link]
Manager briefing pack | All managers | Teams meeting + PDF | Change lead | Change lead | [Date] | [Date] |  | Not started | Impact by team, how to support your people, talking points | [Link]
FAQ published | All staff | Intranet / Google Site | Change lead | Change lead | [Date] | [Date] |  | Not started | Answers to the top 10 anticipated questions | [Link]
Training dates confirmed | All impacted staff | Email | Training lead | Training lead | [Date] | [Date] |  | Not started | When, how, and what to expect from training | [Link]
Go-live announcement | All users | Email + Teams | Exec sponsors | Exec sponsors | [Date] | [Date] |  | Not started | We are live. Here is where to go for help | [Link]
Hypercare week 1 bulletin | All users | Email | Change lead | Change lead | [Date] | [Date] |  | Not started | Known issues, workarounds, support channels | [Link]
Post go-live survey | All impacted staff | Google Form | Change lead | Change lead | [Date] | [Date] |  | Not started | How is it going? What do you still need? | [Link]
BAU handover announcement | All staff | Email | Business owner | Business owner | [Date] | [Date] |  | Not started | Project closing. Here is who to contact going forward | [Link]

## Instructions
How to use this template
This plan follows the format used in the WFU Position Management project communications.
Every communication must have an "Approved by" before sending.
Brief managers 24-48 hours before all-staff communications go out.
Store all draft and final comms in one shared folder. Link from the "Link to asset" column.
Never go more than 2 weeks without communicating, even if there is no news.