## Cutover Plan
Cutover Plan ¦ Wake Forest University
Step-by-step plan for migration to production. Execute on go-live day.
Step # | Task | Owner | Planned time | Actual time | Duration | Dependencies | Status | Rollback plan | Notes
1 | Confirm all pre-conditions met | PM | [Time] |  |  |  | Not started
2 | Take system offline / restrict access | Tech lead | [Time] |  |  | 1 | Not started | Restore access
3 | Execute configuration migration | Tech lead | [Time] |  |  | 2 | Not started | Revert to backup
4 | Update security and access controls | Tech lead | [Time] |  |  | 3 | Not started | Revert security
5 | Run data validation checks | Tech lead | [Time] |  |  | 4 | Not started
6 | Smoke test with core users | PM + testers | [Time] |  |  | 5 | Not started
7 | Open system / restore access | Tech lead | [Time] |  |  | 6 | Not started
8 | Send go-live announcement | Comms lead | [Time] |  |  | 7 | Not started
9 | Activate hypercare support | Change lead | [Time] |  |  | 8 | Not started