## Project Closure Checklist
Project Closure Checklist ¦ Wake Forest University
Complete all items before formally closing the project.
Category | Checklist item | Owner | Status | Completed date | Notes
Handover | Onboarding materials updated for new starters | Change lead | Not started
Handover | Support team briefed with FAQ and known issues | Change lead | Not started
Handover | Governance model confirmed and owner identified | PM | Not started
Comms | Final all-staff communication sent | Comms lead | Not started
Documentation | All project docs archived in shared folder | PM | Not started
Documentation | Decision log complete and stored | PM | Not started
Documentation | Lessons learned report written | PM | Not started
Review | PIR presented to sponsor and leadership | PM | Not started
Review | User survey completed and analyzed | Change lead | Not started
Review | Adoption metrics confirmed above target | Change lead | Not started
Close | Sponsor sign-off on project closure | PM | Not started
Close | 6-month health check reminder set | PM | Not started
Close | Team recognized and thanked | PM | Not started