## Project Plan
Project Plan ¦ Wake Forest University
Combined project and change management milestones. Update status weekly.
# | Phase | Milestone | Type | Owner | Start | Target date | Actual date | Status | Dependencies | Notes
1 | 0. Planning | Define scope and write project charter | PM | [Name] | [Date] | [Date] |  | Not started
2 | 0. Planning | Define project team and roles | PM | [Name] | [Date] | [Date] |  | Not started | 1
3 | 0. Planning | Identify stakeholders | CM | [Name] | [Date] | [Date] |  | Not started | 1
4 | 0. Planning | Create project plan and timeline | PM | [Name] | [Date] | [Date] |  | Not started | 1, 2
5 | 0. Planning | Kick-off meeting | PM | [Name] | [Date] | [Date] |  | Not started | 4
6 | 0. Planning | Set up governance and comms | CM | [Name] | [Date] | [Date] |  | Not started | 3
7 | 1. Discovery | Map current state (as-is) | PM | [Name] | [Date] | [Date] |  | Not started | 5
8 | 1. Discovery | Identify impacted processes, users, systems | PM | [Name] | [Date] | [Date] |  | Not started | 7
9 | 1. Discovery | Stakeholder and impact assessment | CM | [Name] | [Date] | [Date] |  | Not started | 3, 7
10 | 2. Design | Design future state | PM | [Name] | [Date] | [Date] |  | Not started | 7, 8
11 | 2. Design | Define governance, policies, RACI | PM | [Name] | [Date] | [Date] |  | Not started | 10
12 | 2. Design | Launch communication plan | CM | [Name] | [Date] | [Date] |  | Not started | 9
13 | 3. Build | Build system config and process changes | PM | [Name] | [Date] | [Date] |  | Not started | 10, 11
14 | 3. Build | Develop training materials and plan | CM | [Name] | [Date] | [Date] |  | Not started | 12
15 | 4. Test | Test with real users (UAT) | PM | [Name] | [Date] | [Date] |  | Not started | 13
16 | 4. Test | Deliver training and track completion | CM | [Name] | [Date] | [Date] |  | Not started | 14
17 | 5. Go-live | Go-live readiness check and launch | PM | [Name] | [Date] | [Date] |  | Not started | 15, 16
18 | 5. Go-live | Hypercare support active | CM | [Name] | [Date] | [Date] |  | Not started | 17
19 | 6. Close | Post-implementation review | PM | [Name] | [Date] | [Date] |  | Not started | 18
20 | 6. Close | Embed change and transition to BAU | CM | [Name] | [Date] | [Date] |  | Not started | 19