## 1. Master Plan
Change Management Master Plan
Top-level tracker — one row per milestone. Replace [placeholders] with your project details.
# | Milestone | Change type | Phase | Owner | Target date | Actual date | Status | Notes / blockers
1 | Kick-off & executive sponsor alignment | All | Pre go-live | Project manager | [Date] |  | Not started | Confirm sponsor, project lead, and CM lead
2 | Stakeholder mapping complete | All | Pre go-live | Change lead | [Date] |  | Not started | Document in Stakeholder Register sheet
3 | Change impact assessment complete | All | Pre go-live | Change lead | [Date] |  | Not started | Use impact scoring — High / Medium / Low
4 | Communication plan approved | All | Pre go-live | Comms lead | [Date] |  | Not started | See Comms Tracker sheet
5 | Change champion network formed | All | Pre go-live | Change lead | [Date] |  | Not started | At least one champion per impacted team
6 | Training needs analysis signed off | All | Pre go-live | Training lead | [Date] |  | Not started | See Training Tracker sheet
7 | Training materials built & piloted | All | Pre go-live | Training lead | [Date] |  | Not started | Pilot with 5-10 users before full rollout
8 | Go-live readiness check complete | All | Go-live | PM + Change lead | [Date] |  | Not started | Confirm all readiness criteria met
9 | Go-live — system / process / policy active | All | Go-live | Project manager | [Date] |  | Not started
10 | Hypercare activated | All | Go-live | Change lead | [Date] |  | Not started | See Hypercare Log sheet
11 | Hypercare period closed | All | Post go-live | Change lead | [Date] |  | Not started | Exit criteria met — hand off to ops
12 | Post-implementation review | All | Post go-live | Change lead | [Date] |  | Not started | Survey users; document lessons learned
13 | Adoption metrics reviewed | All | Post go-live | Change lead | [Date] |  | Not started | See Adoption Tracker sheet
14 | Transition to business-as-usual | All | Post go-live | Business owner | [Date] |  | Not started | Onboarding materials updated; ops team briefed

## 2. Stakeholder Register
Stakeholder Register
Track every stakeholder — their impact level, engagement approach, and last contact.
Stakeholder name | Team / role | Change type | Impact level | Engagement approach | Key concerns | Owner | Last contact | Status | Notes
[Name] | Executive sponsor | All | High | Monthly sponsor review — agenda shared 3 days prior | Strategic alignment, budget, timeline | PM | [Date] | Not started
[Name] | Team manager — [Team A] | Technology | High | Weekly briefing — 30 min standing call | Team readiness, training time, FTE impact | Change lead | [Date] | Not started
[Name] | Team manager — [Team B] | Process | High | Weekly briefing — 30 min standing call | Workflow disruption, exception handling | Change lead | [Date] | Not started
[Name] | Frontline staff representative | Technology / Process | High | Focus groups + monthly Q&A open session | Job impact, workload, ease of use | Change lead | [Date] | Not started | Rotate representative each month
[Name] | IT / Tech lead | Technology | Medium | Bi-weekly WIP — included in project meetings | Technical dependencies, data migration | PM | [Date] | Not started
[Name] | HR partner | Org design | High | Bi-weekly — chair consultation sessions | People risk, legal obligations, morale | Change lead | [Date] | Not started
[Name] | Legal / compliance | Policy | High | As needed — review cycle | Regulatory requirements, liability | PM | [Date] | Not started
[Name] | Training team | All | Medium | Weekly — build materials together | Capacity, tool access, user readiness | Training lead | [Date] | Not started
[Name] | Change champion — [Team A] | All | Medium | Bi-weekly champion network call | Peer resistance, questions from team | Change lead | [Date] | Not started
[Name] | Change champion — [Team B] | All | Medium | Bi-weekly champion network call | Peer resistance, questions from team | Change lead | [Date] | Not started

## 3. Comms Tracker
Communications Tracker
Plan and track every communication from kick-off to hypercare close.
Communication title | Audience | Channel | Owner | Planned date | Sent date | Status | Key message (one line) | Link to asset
Project announcement — why this change | All staff | Email + intranet post | Exec sponsor | [Date] |  | Not started | Why this change is happening, what it means for you, and what comes next | [Link]
Manager briefing pack | All people managers | Teams meeting + PDF | Change lead | [Date] |  | Not started | Detailed impact by team, how to support your people, talking points | [Link]
FAQ document published | All staff | Intranet / SharePoint | Change lead | [Date] |  | Not started | Answers to the top 10 questions we anticipate | [Link]
Training dates confirmed | All impacted staff | Email | Training lead | [Date] |  | Not started | When and how to complete training before go-live | [Link]
4-week countdown update | All impacted staff | Email + Teams post | Comms lead | [Date] |  | Not started | Progress update, what to expect at go-live, final training reminder | [Link]
1-week countdown reminder | All users | Email | Comms lead | [Date] |  | Not started | Go-live is next [day]. Here is what you need to do on day 1 | [Link]
Go-live announcement | All users | Email + poster + Teams | Exec sponsor | [Date] |  | Not started | We are live! Here is where to go for help today | [Link]
Week 1 hypercare bulletin | All users | Email | Change lead | [Date] |  | Not started | Known issues, workarounds, and where to get support | [Link]
Week 2 update | All users | Email | Change lead | [Date] |  | Not started | Progress update, resolved issues, upcoming drop-in sessions | [Link]
Post go-live survey | All impacted staff | Survey link via email | Change lead | [Date] |  | Not started | How is the change going? What do you still need? | [Link]
Month 2 adoption update | All staff | Email + dashboard | Change lead | [Date] |  | Not started | Adoption metrics, success stories, remaining support options | [Link]
BAU handover announcement | All staff | Email | Business owner | [Date] |  | Not started | The project is closing — here is who to contact going forward | [Link]

## 4. Training Tracker
Training Tracker
Track training design, delivery, and completion by audience. Update completion % weekly.
Training module | Change type | Audience | Format | Duration | Owner | Delivery date | # Invited | # Completed | Completion % | Status | Notes
Overview: what is changing and why (all staff) | All | All staff | Email / video | 5 min | Change lead | [Date] |  |  |  | Not started | Send before any detailed training
Manager briefing: how to support your team | All | All managers | Live workshop | 60 min | Change lead | [Date] |  |  |  | Not started | Run before all-staff sessions
Role-based training: [Role A] e.g. finance team | Technology | [Team A] | Hands-on sandbox workshop | 2 hrs | Training lead | [Date] |  |  |  | Not started | Requires sandbox environment access
Role-based training: [Role B] e.g. operations | Technology | [Team B] | Hands-on sandbox workshop | 90 min | Training lead | [Date] |  |  |  | Not started
Process walkthrough: new workflow | Process | All impacted staff | Live demo + Q&A | 45 min | Process owner | [Date] |  |  |  | Not started | Record session for those who cannot attend
Policy awareness: what the policy means for you | Policy | All staff | E-learning module | 20 min | HR / Compliance | [Date] |  |  |  | Not started | Requires digital acknowledgment on completion
Quick reference guide (self-service) | Technology | All users | PDF / intranet page | Self-serve | Training lead | [Date] | N/A | N/A | N/A | Not started | Publish 2 weeks before go-live
Refresher drop-in (post go-live week 2) | All | All users | 30-min webinar | 30 min | Training lead | [Date] |  |  |  | Not started | Record and post to intranet
New-starter induction module (BAU ongoing) | All | New starters | E-learning | 45 min | Training lead | [Date] | N/A | N/A | N/A | Not started | Add to onboarding portal before project closes

## 5. Hypercare Log
Hypercare Issue Log
Log every issue, query, and risk raised during hypercare. Review daily with the hypercare team.
# | Date raised | Issue / query | Raised by | Team | Category | Priority | Owner | Resolution / action | Status | Date resolved | Comms needed?
1 | [Date] | [Describe the issue or query in plain language] | [Name] | [Team] | System bug | High | IT lead | [Action taken or planned] | Not started |  | Yes
2 | [Date] | [Describe the issue or query in plain language] | [Name] | [Team] | Training gap | Medium | Change lead | [Action taken or planned] | In progress |  | Yes
3 | [Date] | [Describe the issue or query in plain language] | [Name] | [Team] | Process question | Low | Process owner | [Action taken or planned] | Complete | [Date] | No
4 | [Date] | [Describe the issue or query in plain language] | [Name] | [Team] | Data / access issue | High | IT lead | [Action taken or planned] | Not started |  | Yes
5 | [Date] | [Describe the issue or query in plain language] | [Name] | [Team] | Policy question | Medium | HR | [Action taken or planned] | Not started |  | No

## 6. Adoption Tracker
Adoption Tracker
Monitor adoption metrics week by week after go-live. Update every Friday. Target: 80% adoption by week 4.
Period | Active users | Total users | Adoption % | Issues raised (week) | Issues resolved (week) | Issues outstanding (cumul.) | Sentiment score (1-5) | Hypercare / BAU actions | RAG status
Week 1 (go-live) | [7 empty] | Hypercare team on floor / chat. Daily issue log review. | [R/A/G]
Week 2 | [7 empty] | Drop-in webinar. Publish FAQ update. | [R/A/G]
Week 3 | [7 empty] | Manager pulse check call. | [R/A/G]
Week 4 | [7 empty] | Review hypercare exit criteria. Decide: extend or close? | [R/A/G]
Month 2 | [7 empty] | Post-implementation review. User survey. | [R/A/G]
Month 3 | [7 empty] | BAU transition check. Onboarding materials verified. | [R/A/G]
Month 6 (health check) | [7 empty] | Spot-check adoption. Interview 5-10 users. | [R/A/G]

## 7. Risk & Issues Log
Change Management Risk & Issues Log
Track risks and issues to your CM plan. Review weekly with the project manager.
# | Type | Risk / issue description | Impact if it occurs | Likelihood | Severity | Owner | Mitigation / action | Status | Review date | Notes
1 | Risk | Key stakeholders not engaged early — project perceived as IT-led only | Low buy-in, resistance at go-live, adoption failure | Medium | High | Change lead | Confirm exec sponsor by week 2. Run stakeholder workshop in month 1. | Not started | [Date]
2 | Risk | Training delivered too close to go-live — users forget before they use the system | Low confidence, high support ticket volume in hypercare | Medium | Medium | Training lead | Complete all training minimum 2 weeks before go-live. | Not started | [Date]
3 | Risk | Change champion network not established or disengaged | Peer influence lost; resistance spreads unchecked | Low | High | Change lead | Confirm champions by month 2. Run monthly champion briefings. | Not started | [Date]
4 | Risk | Communications delayed or inconsistent — rumours fill the gap | Anxiety, misinformation, loss of trust in leadership | Medium | High | Comms lead | Publish comms calendar. No gap longer than 2 weeks between updates. | Not started | [Date]
5 | Risk | Go-live date changes after training is delivered — knowledge gap | Users trained on wrong version or too early | Low | Medium | PM | Include go-live date risk in project schedule. Refresher plan in place. | Not started | [Date]
6 | Issue | [Describe current issue] | [Impact if not resolved] |  | High | [Owner] | [Action] | Not started | [Date]

## READ ME
Change Management Smartsheet Pack — How to Use
SHEET | PURPOSE
1. Master Plan | Top-level milestone tracker. One row per major CM milestone. Update status weekly in your project stand-up.
2. Stakeholder Register | Log every stakeholder. Record impact level, engagement approach, and last contact date. Revisit monthly.
3. Comms Tracker | Plan every communication. Track planned vs actual send dates. Link to the asset (doc, email, slide deck).
4. Training Tracker | Track training modules, audiences, and completion rates. The Completion % column calculates automatically.
5. Hypercare Log | Log every issue and query raised at go-live. Review daily during hypercare. Close when exit criteria are met.
6. Adoption Tracker | Weekly adoption metrics. Adoption % and cumulative outstanding issues calculate automatically.
7. Risk & Issues Log | Track risks to your CM plan. Review weekly with the PM. Escalate High severity risks immediately.
HOW TO SET UP IN SMARTSHEET
1. Create a new Smartsheet workspace called "[Project name] — Change Management".
2. Import this Excel file or recreate each tab as a new Smartsheet grid in that workspace.
3. Replace all [placeholders] with your project-specific details before sharing.
4. Set up automated reminders on Target date columns in sheets 1, 3, and 4.
5. Share with your project team. Set permissions: Editor for team, Viewer for stakeholders.
6. Create a Smartsheet Dashboard to show a live summary using Sheet Summary from each grid.
7. Review all sheets in your weekly project stand-up. Update Status before each meeting.
COLOUR CODING | MEANING
Not started (grey) | Action not yet begun — on track if before target date
In progress (amber) | Action underway — monitor closely
Complete (green) | Action completed successfully
At risk (red) | Action at risk of missing target — escalate immediately
High impact (red) | High severity stakeholder, risk, or issue
Medium impact (amber) | Moderate severity — monitor and manage
Low impact (green) | Low severity — routine tracking
TIPS FOR NON-EXPERTS
Start change management at project kick-off — not at go-live.
Communicate the "why" before the "what" or "how". People resist change they do not understand.
Training tells people how. Change management helps them want to. You need both.
Over-communicate. Send updates even when nothing has changed.
Find at least one change champion per impacted team — peer influence is powerful.
Define what "done" looks like before go-live: adoption rate, issue count, sentiment score.
Hypercare is not optional. Issues always spike in the first weeks after go-live.